## 工作表1
Student Mart Website
ID | As a | I want to be able to | so that | Points | Status
1 | Seller | rigister / login into my account | I can advertise the good I want to sell | 1 | To be started
2 | Seller | update and show my personal info | the buyer who is interested would be able to contact me | 1 | To be started
3 | Seller | update details about the goods I'm posting | I would be able to catch more eyes | 2 | To be started
4 | Seller | have a payment gateway | I can secure my transaction | 3 | To be started
5 | Seller | show the original price and the used price | buyers have a better picture about how much I'm cutting | 2 | To be started
6 | Seller | report inappropriate activities to admin | we can keep this website neat and clean | 3 | To be started
7 | Admin | remove inappropriate items | no illegals trading will occur | 2 | To be started
8 | Admin | ban users who has violated the rules of the website | we can keep the website neat and clean | 2 | To be started
9 | Admin | access to a page that shows statistics about the website | I can have a better picture of how's the website running | 4 | To be started
10 | Admin | chat with any users who may have questions or issues | I can help them out | 3 | To be started
11 | Admin | send out broadcast | every user will be aware of the latest news or informations | 2 | To be started
12 | Buyer | login to the web application | I can view / compare / buy items | 1 | To be started
13 | Buyer | give review and ratings | I can express clearly about my experience with the buyer | 3 | To be started
14 | Buyer | share my post through other social apps or websites | others that aren't the user of the website would be able to notice my post | 4 | To be started
15 | Buyer | access to the detail page of the item | I can have a better picture of what the item really is and if it is something I need | 3 | To be started
16 | Buyer | add items to my list | I can easily check the item which I'm interested in | 3 | To be started
17 | Buyer | have a secured way to pay | my money will end up being in the right one's hand | 4 | To be started
|  |  | Total | 43